## PBI
Folder | Owner | Requestor | Report Name | Drill through | Report Template | Current status | Sources | Work in Progress / Expected date | Link to report (if available) | #Views | #Users
Working on
Claim | CLAIM | Mr. George | Claim monthly non-disclosure report |  |  | 20% | SQL | ETA May 20,2022 to have beta version - There was a meeting with Claim and Actuarial on March 24, 2022 to clarify how to calculate related fields
Claim | CLAIM | Mr. George | Upgrade Claim A/E Report to include FYP for all AD levels |  |  | 60% | SQL, Excel | ETA May 20, 2022 to have beta version - Complete the data processing into the model. Cross checking with the processed Actuarial file. - Finished about 60%
BOM | BOM | Mr. George | Free look lapse % |  |  | In progress | SQL
AC | AC | Ms. Tram | Upgrade: Compliance analysis of AD | TD->AD |  | In progress | Excel | ETA Mar/2022 --> update ETA May/2022 Current report using Excel, need to upgrade using SQL | http://pbi.phuhunglife.com/reports/powerbi/AC/Compliance%20Report
CS - CC | CS - CC | Ms. Vui | Upgrade: Call Center Report (CC Productivity) | TD -> AD |  | In progress | SQL (Odoo & 3CX) | ETA April/2022 --> update ETA May/2022 Redesign current report and data visualizes | http://pbi.phuhunglife.com/reports/powerbi/CS-CC/CallCenter%20Report | 11 | 4
DP | AD | Mr. Dat | MDRT report | TD -> AD | Done | 90% | SQL | Cross check data & enhance
DP | AD | Mr. Dat | Hoi An Trip report | TD -> AD | Done | 90% | SQL | Cross check data & enhance
Pipeline
PS | PS | Ms. Ngoc | Change request Impact Premium report (Analysis on impact from customers' change requests) |  |  | Open | SQL, Excel | Initial analysis of Excel / PPT file prepared by SE and ACT ETA April/2022 to have beta version
PS | PS | Ms. Ngoc | Premium Collection (Analysis on RYP collection) |  |  | Open | SQL, Excel
PS | PS | Ms. Ngoc | PS TAT report (deparmental productivity) | TD -> Sale Office / AD |  | Open | Excel (Manual) | Current using Excel datasource, need to upgrade using SQL
PS | PS | Ms. Ngoc | Upgrade: Summary Report | TD -> Sale Office / AD |  | Open | Excel (Manual) |  | http://pbi.phuhunglife.com/reports/powerbi/PS/1_SUMMARY%20REPORT
PS | PS | Ms. Ngoc | Upgrade: Transaction Report | TD -> Sale Office / AD |  | Open | Excel (Manual) |  | http://pbi.phuhunglife.com/reports/powerbi/PS/2_TRANSACTION_REPORT
PS | PS | Ms. Ngoc | Upgrade: Territory Report | TD -> Sale Office / AD |  | Open | Excel (Manual) |  | http://pbi.phuhunglife.com/reports/powerbi/PS/3_TERRITORY_REPORT
PS | PS | Ms. Ngoc | Upgrade: Other Report | TD -> Sale Office / AD |  | Open | Excel (Manual) |  | http://pbi.phuhunglife.com/reports/powerbi/PS/4_OTHER_REPORT
SE | SE | Mr. Tung | Premium Collection Analysis on SE team productivity |  |  | Open | SQL, Excel (Odoo) | This report is similar to PS reports, will start when PS reports are done.
DP | AD | Mr. Dat | Pro FC, Rookie Bonus payment |  |  | Open | Excel, SQL | Analysing
DP | AD | Mr. Dat | Wrong payments report |  |  | Open | Excel | Not prioritized due to not automated by SQL
Finished reports - Optimizing - Maintaining
AC | AC | Ms. Tram | Compliance analysis of AD | TD->AD | Done | Finish | Excel | Done | http://pbi.phuhunglife.com/reports/powerbi/AC/Compliance%20Report | 3 | 2
BOM | BOM | GD | AD productivity (GD's template) | TD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/BOM/2_TD%20Productivity | 15 | 5
BOM | BOM | GD | Cash Collection by submitting sales office (CS data) | TD -> Sales Office -> AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/DP/1_CS%20Application%20-%20Premium | 6 | 3
CLAIM | CLAIM | Mr. Nam | Claim TAT report | TD -> Sale Office / AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/CLAIM/1_TAT%20REPORTS | 19 | 5
CLAIM | CLAIM | Mr. Nam | Claim Settlement Report | TD -> Sale Office / AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/CLAIM/2_SETTLEMENT%20REPORTS | 7 | 3
CLAIM | CLAIM | Mr. Nam | Claim Trend Report | TD -> Sale Office / AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/CLAIM/3_TREND%20REPORTS | 10 | 4
CLAIM | CLAIM | Mr. Nam | Claim Pending Report | TD -> Sale Office / AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/CLAIM/4_PENDING%20REPORTS | 11 | 4
CLAIM | CLAIM | Mr. Nam | Claim Ratio Actual Expectation Report | TD -> Sale Office / AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/CLAIM/5_CLAIM_RATIO_A_E | 19 | 5
CLAIM | CLAIM | Mr. Nam | Early Claim Report | TD -> Sale Office / AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/CLAIM/6_EARLY_CLAIM | 10 | 5
DP | AD | Mr. Dat | Cash Collection by submitting sales office (CS data) | TD -> Sales Office -> AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/DP/1_CS%20Application%20-%20Premium | 50 | 26
DP | AD | Mr. Dat | Daily sales agency report (Data from DA-DP) | TD -> AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/DP/2_Sale%20Performance | 58 | 28
DP | AD | Mr. Dat | Agency Manpower report | TD -> AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/DP/3_Manpower | 40 | 23
DP | AD | Mr. Dat | K2_AD report | TD -> AD | Done | Finish for latest month data | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/DP/4_K2 | 102 | 27
DP | AD | Mr. Dat | DT Active (for DT team to analyze performance of newly recruited agents) | TD -> AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/DP/5_DT%20Active | 24 | 13
NB | NB | Mr. Hoang | Daily Sale Report (Data from NBU) | TD -> Sale Office / AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/NB/1_DAILY_SALE_REPORT | 22 | 2
NB | NB | Mr. Hoang | NBU TAT report - Clean Case / Non Clean case (departmental productivity) | TD -> Sale Office / AD | Done | Finish | SQL | Done | http://pbi.phuhunglife.com/reports/powerbi/NB/2_TAT_REPORT | 7 | 4